## salemkarani@gmail.com
Title | Start | End | Duration | Description
Opengl WRITE CODE + tutorial | 10/22/2013 20:45 | 10/22/2013 22:45 | 02:00
Program Opengl-finish tutorials 7-9 | 10/23/2013 08:30 | 10/23/2013 11:00 | 02:30
Program Opengl-finish tutorials 10-13 | 10/24/2013 08:30
Program Opengl-finish tutorials 13-17, FINAL | 10/25/2013 08:30 | 10/24/2013 11:00 | 02:30
Program Opengl-finish writing trig panel lib/functions | 10/26/2013 08:30 | 10/25/2013 11:00 | 02:30
Program Opengl-get ui beta working, then make lib of funct. | 10/27/2013 08:30 | 10/26/2013 11:00 | 02:30
Program Opengl-fonts/text | 10/28/2013 08:30 | 10/27/2013 11:00 | 02:30
Program Opengl-backgrounds/texture mapping | 10/29/2013 08:30 | 10/28/2013 11:00 | 02:30
Program Opengl-blur/shadows | 10/30/2013 08:30 | 10/29/2013 11:00 | 02:30
Program Opengl-blur/shadows | 10/31/2013 08:30 | 10/30/2013 11:00 | 02:30
Program Opengl-event handling/buttons | 11/01/2013 08:30 | 10/31/2013 11:00 | 02:30
Program Opengl-event handling | 11/02/2013 08:30 | 11/01/2013 11:00 | 02:30
Program Opengl-beta layout | 11/03/2013 08:30 | 11/02/2013 11:00 | 02:30
Program Opengl-animations | 11/04/2013 08:30 | 11/03/2013 11:00 | 02:30
Program Opengl-music player (?) | 11/05/2013 08:30 | 11/04/2013 11:00 | 02:30
Program Opengl-finish beta | 11/06/2013 08:30 | 11/05/2013 11:00 | 02:30
Program Opengl-serverside | 11/07/2013 08:30 | 11/06/2013 11:00 | 02:30
Program Opengl-serverside + conformit across linux computers | 11/08/2013 08:30 | 11/07/2013 11:00 | 02:30
Program Opengl-get ui beta working+ work on lib of funct. | 11/09/2013 08:30 | 11/08/2013 11:00 | 02:30
Program Opengl-release build | 11/10/2013 08:30 | 11/09/2013 11:00 | 02:30
Program Opengl-library | 11/11/2013 08:30 | 11/10/2013 11:00 | 02:30
Program Opengl-update layout | 11/12/2013 08:30 | 11/11/2013 11:00 | 02:30
Program Opengl-client side | 11/13/2013 08:30 | 11/12/2013 11:00 | 02:30
|  | Total: | 160:15